## Instructie
Manual
Think before you act, do not remove formulas from the sheets ( check first )
First use
| Fill in the Project, Class and Team name in sheet Total | Vul de naam van het project en de klas en groep in op de tab "Totaal"
| Fill in the usernames for the students, remove unused names | Daarna eveneens de namen van de 4 studenten
Need more activity lines in some week |  | Meer activiteitregels nodig in een week?
| Copy the last line and insert it before the total line | Maak een kopie van de laatste activiteitregel en voeg deze in voor de totaalregel

## Total
Time registration |  | Students | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Total
Project : | Scorion Audio Feedback | Julie Kuttschreutter | 6 | 8 | 11.5 | 12.75 | 3.5 | 0 | 0 | 0 | 41.75
|  | Syandana Suntana | 5.5 | 6 | 7 | 8.75 | 3 | 0 | 0 | 0 | 30.25
Class & Team | DHI2V.So & Group 3v | Maksim Sadkov | 4.75 | 9 | 10.5 | 11 | 5.75 | 0 | 0 | 0 | 41
|  | Simona Waxmann | 5.5 | 5 | 9 | 9.25 | 6.5 | 0 | 0 | 0 | 35.25
|  | Mihaela Stoyanova | 5.5 | 5.7 | 8.8 | 10.05 | 4 | 0 | 0 | 0 | 34.05
|  | Danylo Kurbatov | 5.5 | 6.5 | 8 | 6 | 0 | 0 | 0 | 0 | 26
|  | Weektotal | 32.75 | 40.2 | 54.8 | 57.8 | 22.75 | 0 | 0 | 0
|  | Sprinttotal | Week 2: 72.95; Week 4: 112.6; Week 6: 22.75; Week 8: 0
|  | Hours to burn | 543.25 | 503.05 | 448.25 | 390.45 | 367.7 | 367.7 | 367.7 | 367.7
Available hours per week : | 72 | Total Hours available | 576 | 504 | 432 | 360 | 288 | 216 | 144 | 72

## Week (1)
Week 1 | Uren TOTAAL
Julie Kuttschreutter | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff / classes | 2 |  |  | 2 |  |  | 4
Testing out recording API |  |  |  | 0.5 |  | 1 | 1.5
Scrum meetings | [5 empty] | 0.5 | 0.5
0
0
Total | 2 | 0 | 0 | 2.5 | 0 | 1.5 | 6
Syandana Suntana | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff/Classes | 2 |  |  | 2 |  |  | 4
GitLab issue board |  |  | 1 |  |  |  | 1
Scrum meetings | [5 empty] | 0.5 | 0.5
0
0
Total | 2 | 0 | 1 | 2 | 0 | 0.5 | 5.5
Maksim Sadkov | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff / classes | 2 |  |  | 2 |  |  | 4
Gitlab repository setup | 0.25 | [5 empty] | 0.25
Scrum meetings | [5 empty] | 0.5 | 0.5
0
0
Total | 2.25 | 0 | 0 | 2 | 0 | 0.5 | 4.75
Simona Waxmann | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff/Classes | 2 |  |  | 2 |  |  | 4
Definition of done - documentation |  |  |  | 1 |  |  | 1
Scrum meetings | [5 empty] | 0.5 | 0.5
0
0
Total | 2 | 0 | 0 | 3 | 0 | 0.5 | 5.5
Mihaela Stoyanova | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff/Classes | 2 |  |  | 2 |  |  | 4
Code of conduct | 1 | [5 empty] | 1
SCRUM meetings | [5 empty] | 0.5 | 0.5
0
0
Total | 3 | 0 | 0 | 2 | 0 | 0.5 | 5.5
Danylo Kurbatov | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff / Classes | 2 |  |  | 2 |  |  | 4
Scrum meetings | [5 empty] | 0.5 | 0.5
Creating project structure |  |  |  | 1 |  |  | 1
0
0
Total | 2 | 0 | 0 | 3 | 0 | 0.5 | 5.5
Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Week (2)
Week 2 | Uren TOTAAL
Julie Kuttschreutter | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Writing introduction of Functional Design | 3 | [5 empty] | 3
Classes | 2 | [5 empty] | 2
Meeting with Scorion |  |  |  | 1.5 |  |  | 1.5
Group meeting |  |  |  | 1 |  | 0.5 | 1.5
0
Total | 5 | 0 | 0 | 2.5 | 0 | 0.5 | 8
Syandana Suntana | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
User story creation for Functional Design | 1 |  |  | 1 |  |  | 2
Group meeting | [5 empty] | 0.5 | 0.5
Classes | 2 | [5 empty] | 2
Scorion meeting |  |  |  | 1.5 |  |  | 1.5
0
Total | 3 | 0 | 0 | 2.5 | 0 | 0.5 | 6
Maksim Sadkov | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Classes | 2 | [5 empty] | 2
Writing inital part of the System Design document | 1 | 1.5 |  | 1.5 |  |  | 4
Scorion meeting |  |  |  | 1.5 |  |  | 1.5
Group meeting |  |  |  | 1 |  | 0.5 | 1.5
0
Total | 3 | 1.5 | 0 | 4 | 0 | 0.5 | 9
Simona Waxmann | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Classes | 2 | [5 empty] | 2
Scrum meetings |  |  |  | 1 |  | 0.5 | 1.5
Scorion meeting |  |  |  | 1.5 |  |  | 1.5
0
0
Total | 2 | 0 | 0 | 2.5 | 0 | 0.5 | 5
Mihaela Stoyanova | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Classes | 2 | [5 empty] | 2
Functional design - wireframes | 0.4 |  |  | 0.3 |  |  | 0.7
SCRUM meeting |  |  |  | 1 |  | 0.5 | 1.5
Scorion meeting |  |  |  | 1.5 |  |  | 1.5
0
Total | 2.4 | 0 | 0 | 2.8 | 0 | 0.5 | 5.7
Danylo Kurbatov | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Classes | 2 |  | 2 |  |  |  | 4
Writing Solution overviewof Functional Design | 1 |  | 1 |  |  |  | 2
Group meeting | [5 empty] | 0.5 | 0.5
0
0
Total | 3 | 0 | 3 | 0 | 0 | 0.5 | 6.5
Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Week (3)
Week 3 | Uren TOTAAL
Julie Kuttschreutter | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Classes | 2 |  |  | 2 |  |  | 4
Researching APIs for recording audio |  | 1 |  |  |  |  | 1
Creating prototype in Figma |  | 1.5 |  |  |  |  | 1.5
Working on audio recording functionality |  |  |  | 2 |  | 3 | 5
0
Total | 2 | 2.5 | 0 | 4 | 0 | 3 | 11.5
Syandana Suntana | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Classes | 2 |  |  | 2 |  |  | 4
Creating database diagram |  |  | 1 |  |  |  | 1
User story refining |  | 2 |  |  |  |  | 2
0
0
Total | 2 | 2 | 1 | 2 | 0 | 0 | 7
Maksim Sadkov | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Classes | 2 |  |  | 2 |  |  | 4
Researching tools that can be used for speech-to-text transription | 1 | [5 empty] | 1
Team meetings |  | 0.5 |  |  |  |  | 0.5
Setting up product backlog |  | 0.5 |  |  |  |  | 0.5
Working on audio transcription functionality |  |  |  | 1.5 |  | 3 | 4.5
Total | 3 | 1 | 0 | 3.5 | 0 | 3 | 10.5
Simona Waxmann | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Classes | 2 |  |  | 2 |  |  | 4
Scrum meetings |  | 0.5 |  |  |  |  | 0.5
Setup templates for the UI |  |  | 4.5 |  |  |  | 4.5
0
0
Total | 2 | 0.5 | 4.5 | 2 | 0 | 0 | 9
Mihaela Stoyanova | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Classes | 2 |  |  | 2 |  |  | 4
Scrum meetings |  | 0.5 |  |  |  |  | 0.5
UI component for assigment |  | 2 | 1 | 0.3 |  |  | 3.3
Create audio file component | [5 empty] | 1 | 1
0
Total | 2 | 2.5 | 1 | 2.3 | 0 | 1 | 8.8
Danylo Kurbatov | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | 2 |  |  | 2 |  |  | 4
Scrum meetings |  | 0.5 |  |  |  |  | 0.5
Endpoints and rest specification | [5 empty] | 3.5 | 3.5
0
0
Total | 2 | 0.5 | 0 | 2 | 0 | 3.5 | 8
Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Week (4)
Week 4 | Uren TOTAAL
Julie Kuttschreutter | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Group Meetings | 1 |  | 1 | 1 |  |  | 3
Working on audio recording functionality | 2 | 2 |  | 2 | 2 | 1 | 9
Scorion Meeting |  |  |  | 0.75 |  |  | 0.75
0
0
Total | 3 | 2 | 1 | 3.75 | 2 | 1 | 12.75
Syandana Suntana | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Group meetings | 1 |  |  | 1 |  |  | 2
Working on database |  | 1 | 2 |  |  |  | 3
Scorion Meeting |  |  |  | 0.75 |  |  | 0.75
Changing database |  |  |  |  | 1 | 2 | 3
0
Total | 1 | 1 | 2 | 1.75 | 1 | 2 | 8.75
Maksim Sadkov | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Group meetings | 1 |  | 1 | 1 |  |  | 3
Working on audio transcription functionality | 1 | [5 empty] | 1
Working on the automatic punctuation in transcribed text | 3 | [5 empty] | 3
Switching to whisper AI model for transription | [5 empty] | 4 | 4
0
Total | 5 | 0 | 1 | 1 | 0 | 4 | 11
Simona Waxmann | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Scrum meetings | 1 |  | 1 | 1 |  |  | 3
Implement early database | 2 | [5 empty] | 2
Create presentation for the meeting with the client |  |  | 2 |  |  |  | 2
Scorion meeting |  |  |  | 0.75 |  |  | 0.75
Change main theme color from black to white |  |  |  |  | 1 | 0.5 | 1.5
Total | 3 | 0 | 3 | 1.75 | 1 | 0.5 | 9.25
Mihaela Stoyanova | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
SCRUM meerings | 2 |  |  | 1.3 |  |  | 3.3
Create presentation for meeting with the client |  | 2 |  | 1 |  |  | 3
Create audio file component | 1 | 2 |  |  |  |  | 3
Scorion meeting |  |  |  | 0.75 |  |  | 0.75
0
Total | 3 | 4 | 0 | 3.05 | 0 | 0 | 10.05
Danylo Kurbatov | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
Scrum meetings | 2 |  |  | 1 |  |  | 3
Testing puncruality |  |  | 2 |  |  |  | 2
Scorion meeting |  |  |  | 1 |  |  | 1
0
Total | 2 | 0 | 2 | 2 | 0 | 0 | 6
Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Week (5)
Week 5 | Uren TOTAAL
Julie Kuttschreutter | Uren
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Class | 2.5 | [5 empty] | 2.5
Documentation |  | 1 |  |  |  |  | 1
0
0
0
Total | 2.5 | 1 | 0 | 0 | 0 | 0 | 3.5
Syandana Suntana | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Class | 2 | [5 empty] | 2
Documentation |  | 1 |  |  |  |  | 1
0
0
0
Total | 2 | 1 | 0 | 0 | 0 | 0 | 3
Maksim Sadkov | Uren
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Classes | 2.5 | [5 empty] | 2.5
Team meetings |  |  | 0.5 | 0.5 |  |  | 1
Switching to whisper AI model for audio transcription | 2.25 | [5 empty] | 2.25
0
0
Total | 4.75 | 0 | 0.5 | 0.5 | 0 | 0 | 5.75
Simona Waxmann | Uren
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Classes | 2 | [5 empty] | 2
Scrum meetings |  |  | 1 | 0.5 |  |  | 1.5
Write system architecture in system design |  |  | 3 |  |  |  | 3
0
0
Total | 2 | 0 | 4 | 0.5 | 0 | 0 | 6.5
Mihaela Stoyanova | Uren
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Classes | 2 | [5 empty] | 2
Scrum meetings |  |  | 1 |  |  |  | 1
Write client communication log | 1 | [5 empty] | 1
Re-write requirements based on feedback | [6 empty] | 0
0
Total | 3 | 0 | 1 | 0 | 0 | 0 | 4
Danylo Kurbatov | Uren
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Uren
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Uren
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Uren
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Uren
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Week (6)
Week 6 | Uren TOTAAL
Julie Kuttschreutter | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Syandana Suntana | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Maksim Sadkov | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Simona Waxmann | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Classes | [6 empty] | 0
Scrum meetings | [6 empty] | 0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mihaela Stoyanova | Hours
User story / task description |  | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Danylo Kurbatov | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Week (7)
Week 7 | Uren TOTAAL
Julie Kuttschreutter | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Syandana Suntana | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Maksim Sadkov | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Simona Waxmann | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Classes | [6 empty] | 0
Scrum meetings | [6 empty] | 0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mihaela Stoyanova | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Danylo Kurbatov | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Week (8)
Week 8 | Uren TOTAAL
Julie Kuttschreutter | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Syandana Suntana | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Maksim Sadkov | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Simona Waxmann | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Classes | [6 empty] | 0
Scrum meetings | [6 empty] | 0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mihaela Stoyanova | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Danylo Kurbatov | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0